## Sheet1
4 | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
As, a user I want an application that has various features, so that this app is a one sttop shop for all of my needs | create UI interface and then create the application | 5 | 4 | 3 | 2 | 0
As a user, I want to track my fitness, so that I can monitor my progress and stay consistent with my goals. | develop fitness tracking feature | 4 | 4 | 3 | 3 | 0
As a user, I want to return to the main dashboard, so that I can select other options within the system. | implent a back button to return to the dashboard | 3 | 4 | 3 | 2 | 0
As a user, I want to upload my workout media, so that I can access my photos and videos in the galleray anytime without worrying about losing them. | create a database for media storage and to retrive the media | 5 | 4 | 3 | 2 | 0
As a user, I want to see trending fitness activities and challenges, so that I can stay in the loop and join in on what’s popular. | create trending activities feed option the dashbooard | 5 | 4 | 3 | 2 | 0
As a user, I want to join in on community discussions, so that I can connect with people who have similar fitness goals and stay motivated. | create community forum button on dashboard | 3 | 4 | 3 | 2 | 0
| Estimate Totals | 25 | 24 | 18 | 13 | 0