## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2
Visit and download the webapp from the web page that explains the project scope | Implement a page with project scope details and a download link | 3 | 2 | 1
Click the download button and receive confirmation of a successful download | Add download button functionality and a confirmation page | 2 | 1 | 1
Enter my data for my meals (meal type, date, time, ingredients, calories, protein, carbs, and fat) | Build the meal entry form with all required fields | 4 | 2 | 2
Receive a confirmation message after a successful submission of a meal entry | Display a confirmation message upon successful meal entry submission | 3 | 2 | 1
Receive an error message after an invalid submission due to missing required data | Display a confirmation message upon successful meal entry submission | 5 | 3 | 2
Receive an error message after an invalid submission due to missing required data | Implement inline error handling for invalid or missing required fields | 2 | 1 | 1
Edit existing meal entry | Add functionality to edit/update a previously submitted meal entry | 2 | 1 | 1
View daily and weekly history of my meal entries | Create filtering and summary view to group meal entries by day and week
| Estimate Totals | 21 | 12 | 9